## Sheet1
Task No | Task Description | Status | Assigned To | Notes
I. Documents
| System Requirement Specification | Closed
| Use Case Diagram | Closed
| Class Diagram | Active | Domi
| Front-end design wireframes | Active | Genie
II. Development
Source Control Management Preparation
1 | Git source control of the project | Closed | Domi
Application Framework
2 | Create the required classes based from the class diagram | Active | Domi
Web application functionalities for all users (Home Page)
3 | Create views where any user can see the following important information 1. Information about HMS 2. Information about Navitaire 3. Team Videos 4. Team profiles 5. Mechanics of the voting process 6. Roles involved in the voting process | New | Genie | Still waiting for design wireframes
Log in functionality
4 | Design for the login page | New |  | Still waiting for design wireframes
5 | Administrator can register users as either encoders or auditors | New
6 | Registered encoders or auditors can log in using their credentials | New
7 | Validation of username and password | New
8 | Forgot password functionality | New
9 | Redirect to Home page after logging in | New
Encoder and Administrator functionalities
| Encoder Functionality |  |  | Encoder can only enter payments of his own team Refer to the SSR for the list of the required vote entry informaton
10 | Design for the encode page | New |  | Still waiting for design wireframes
Manual encode functionality (Internal and External)
11 | Encoder can input the required details for the vote entry | Active | Domi | Refer to SSR for the required details
12 | Implement a dropdown for selecting a team voted for | Active | Domi
Implement a dropdown for type of vote entry payment
13 | Encoder can only enter payments of his own team | New
14 | Limit internal payment to Php currency | New
15 | Allow different currencies for external payment | New |  | Ask Lei for accepted currencies
16 | Compute for peso equivalent of each payment | New
17 | Validation for the input details | New
18 | Submit and store the vote entry details in the database | New
Import an excel file functionality
19 | Design for import excel file page | New |  | Still waiting for design wireframes
20 | Browse for a file saved in the local machine | New
21 | Validate the file entered | New |  | Only excel files are allowed
22 | Reads the content of the file and convert it to data accepted by the database | New
23 | Save the data to the database | New
View list of encoded payments
24 | Design of page for viewing list of encoded payments | New
25 | Encoder can only see the votes he/she encoded | New
26 | Retrieve a specific vote entry by entering a voter last name and/or firstname | New
27 | Retrieve a vote entry by entering the amount paid | New
28 | Retrieve a vote entry by entering a voter email address | Active | Domi
29 | Ability to sort the vote entry list in either ascending or descending order | New
Edit encoded payments
30 | In the "View Encoded Entries page", each vote entry should have an Edit link beside it. Redirect to Edit page upon clicking the link | Active | Domi
31 | Layout for the Edit page | New
32 | Show the current property values of the vote entry object in textboxes so that the encoder can edit them | Active | Domi
33 | Validate the input values of the encoder | New
34 | "Are you sure?" question before committing any changes | New
35 | Saving the changes made | New
36 | Redirect to ViewAll page after edit | New
Delete encoded payments
37 | In the "View Encoded Entries page", each vote entry should also have a Delete beside it which deletes the vote entry upon clicking it. | Active
38 | "Are you sure?" question before actually deleting the vote entry | New
39 | Ajax call for deleting vote entries | New
40 | Update list of vote entries after delete process | New
Auditor Functionalities
41 | "View Encoded Entries page" - View the input of all the encoders of their own team | New
42 | Each vote entry in the list will have a checkbox beside it. All the ticked vote entries shall be locked when the "Lock Payments" button is clicked | New |  | This checkbox should be hidden when an encoder is logged in instead of an auditor.
43 | "Lock All Payments" button functionality | New
Administrator Specific functionalities
44 | Design of the Votes Summary page | New |  | Contents of the Votes summary table to be followed
45 | Contents of the votes summary table | New
46 | View all of the votes of the encoded payments | Active | Domi