## Sheet1
Tasks | Status | Final Version | Notes | Task Item | Assigned To
I. Documents
System Requirement Specification | Version 1 complete | No
Use Case Diagram | Version 1 complete | No
Class Diagram | Version 1 complete | No
Front-end design wireframes | In progress
II. Development
Source Control Management Preparation
Git source control of the project | Complete |  |  | 1 | Domi
Application Framework
Create the required classes based from the class diagram | In progress |  |  | 2 | Domi
Web application functionalities for all users (Home Page)
Create views where any user can see the following important information 1. Information about HMS 2. Information about Navitaire 3. Team Videos 4. Team profiles 5. Mechanics of the voting process 6. Roles involved in the voting process | Not yet started |  | Still waiting for design wireframes | 3 | Genie
Log in functionality
Design for the login page | Not yet started |  | Still waiting for design wireframes | 4
Administrator can register users as either encoders or auditors | Not yet started |  |  | 5
Registered encoders or auditors can log in using their credentials | Not yet started |  |  | 6
Validation of username and password | Not yet started |  |  | 7
Forgot password functionality | Not yet started |  |  | 8
Redirect to Home page after logging in | Not yet started |  |  | 9
Encoder and Administrator functionalities
Encoder Functionality |  |  | Encoder can only enter payments of his own team Refer to the SSR for the list of the required vote entry informaton
Design for the encode page | Not yet started |  | Still waiting for design wireframes | 10
Manual encode functionality (Internal and External)
Encoder can input the required details for the vote entry | In progress |  | Refer to SSR for the required details | 11 | Domi
Implement a dropdown for selecting a team voted for | In progress |  |  | 12 | Domi
Encoder can only enter payments of his own team | Not yet started |  |  | 13
Limit internal payment to Php currency | Not yet started |  |  | 14
Allow different currencies for external payment | Not yet started |  | Ask Lei for accepted currencies | 15
Compute for peso equivalent of each payment | Not yet started |  |  | 16
Validation for the input details | Not yet started |  |  | 17
Submit and store the vote entry details in the database | Not yet started |  |  | 18
Import an excel file functionality
Design for import excel file page | Not yet started |  | Still waiting for design wireframes | 19
Browse for a file saved in the local machine | Not yet started |  |  | 20
Validate the file entered | Not yet started |  | Only excel files are allowed | 21
Reads the content of the file and convert it to data accepted by the database | Not yet started |  |  | 22
Save the data to the database | Not yet started |  |  | 23
View list of encoded payments
Design of page for viewing list of encoded payments | Not yet started |  |  | 24
Encoder can only see the votes he/she encoded | Not yet started |  |  | 25
Retrieve a specific vote entry by entering a voter last name and/or firstname | Not yet started |  |  | 26
Retrieve a vote entry by entering the amount paid | Not yet started |  |  | 27
Retrieve a vote entry by entering a voter email address | In progress |  |  | 28 | Domi
Ability to sort the vote entry list in either ascending or descending order | Not yet started |  |  | 29
Edit encoded payments
In the "View Encoded Entries page", each vote entry should have an Edit link beside it. Redirect to Edit page upon clicking the link | In progress |  |  | 30 | Domi
Layout for the Edit page | Not yet started |  |  | 31
Show the current property values of the vote entry object in textboxes so that the encoder can edit them | In progress |  |  | 32 | Domi
Validate the input values of the encoder | Not yet started |  |  | 33
"Are you sure?" question before committing any changes | Not yet started |  |  | 34
Saving the changes made | Not yet started |  |  | 35
Redirect to ViewAll page after edit | Not yet started |  |  | 36
Delete encoded payments
In the "View Encoded Entries page", each vote entry should also have a Delete beside it which deletes the vote entry upon clicking it. | In progress |  |  | 37
"Are you sure?" question before actually deleting the vote entry | Not yet started |  |  | 38
Ajax call for deleting vote entries | Not yet started |  |  | 39
Update list of vote entries after delete process | Not yet started |  |  | 40
Auditor Functionalities
"View Encoded Entries page" - View the input of all the encoders of their own team | Not yet started |  |  | 41
Each vote entry in the list will have a checkbox beside it. All the ticked vote entries shall be locked when the "Lock Payments" button is clicked | Not yet started |  | This checkbox should be hidden when an encoder is logged in instead of an auditor. | 42
"Lock All Payments" button functionality | Not yet started |  |  | 43
Administrator Specific functionalities
Design of the Votes Summary page | Not yet started |  | Contents of the Votes summary table to be followed | 44
Contents of the votes summary table | Not yet started |  |  | 45
View all of the votes of the encoded payments | In progress |  |  | 46 | Domi